## RAID LOG
| RAID Log | [6 empty] | Total | Critical | High | Moderate | Low | Negligible
R1 | Risk | Low prediction accuracy due to synthetic dataset | High | Medium | Improve dataset quality and add relevant features | Pranav Sukale | Open
R2 | Risk | Overfitting of ML model | High | Medium | Use cross-validation and regularization | Pranav Sukale | Open
R3 | Risk | Streamlit UI navigation bugs | Medium | Medium | Continuous UI testing after updates | Pranav Sukale | In Progress
A1 | Assumption | Students provide accurate input data | Medium | - | Add input validation constraints | Pranav Sukale | Valid
A2 | Assumption | Synthetic dataset reflects real trends | High | - | Plan to integrate real dataset later | Pranav Sukale | Valid
I1 | Issue | Top-3 recommendation initially showing single output | Medium | - | Updated logic to return top 3 predictions | Pranav Sukale | Resolved
I2 | Issue | Reset button not clearing selections | Medium | - | Implemented session state reset | Pranav Sukale | Resolved
D1 | Dependency | Clean dataset required before model training | High | - | Complete preprocessing phase first | Pranav Sukale | Active
D2 | Dependency | Trained model required before UI integration | High | - | Finalize model before deployment | Pranav Sukale | Active
R4
R5
R6
A3
A4
I3
D3